## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  |  | 2026-02-05
Project Team Name |  |  | Team Nova
Project Topic |  |  | Intelligent Microservices for Automated Recruitment and Technical Research
Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[9 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[9 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
1. Project Initiation |  |  |  | 2026-01-05 | 2026-01-09 | Swamy (Leader) | Action Plan | Done | bar: 2021-11-01 to 2021-11-05
| 1.1. Project Scoping |  |  | 2026-01-05 | 2026-01-06 | Swamy | Scope Doc | Done | bar: 2021-11-01 to 2021-11-02
|  | 1.1.1. Problem Definition |  | 2026-01-05 | 2026-01-05 | Swamy | Problem Statement | Done | bar: 2021-11-01
|  |  | 1.1.1.1. Define "Dual-AI" Architecture | 2026-01-06 | 2026-01-06 | Devesh | Architecture Diagram | Done | bar: 2021-11-01
| 1.2. Resource Planning |  |  | 2026-01-07 | 2026-01-09 | Swamy | Team Roles | Done | bar: 2021-11-03 to 2021-11-05
|  | 1.2.1. Tech Stack Selection |  | 2026-01-07 | 2026-01-08 | Durga | Tech List (Llama/FAISS) | Done | bar: 2021-11-03 to 2021-11-04
|  |  | 1.2.1.1. Finalize API Keys & Tools | 2026-01-09 | 2026-01-09 | Sakshi | Environment Setup | Done | bar: 2021-11-05
2. Data Engineering |  |  |  | 2026-01-12 | 2026-01-16 | Eswar | Processed Data | Done | bar: 2021-11-06 to 2021-11-10
| 2.1. Data Collection |  |  | 2026-01-12 | 2026-01-13 | Eswar | Raw PDF Folder | Done | bar: 2021-11-06 to 2021-11-07
|  | 2.1.1. Sourcing Resumes (Kaggle/GitHub) |  | 2026-01-12 | 2026-01-12 | Eswar | 50+ Resumes | Done | bar: 2021-11-06
|  |  | 2.1.1.1. Sourcing Research Papers (arXiv) | 2026-01-13 | 2026-01-13 | Eswar | 20+ Papers | Done | bar: 2021-11-07
| 2.2. Data Preprocessing |  |  | 2026-01-14 | 2026-01-16 | Eswar | Cleaned Text | Done | bar: 2021-11-08 to 2021-11-10
|  | 2.2.1. PDF Text Extraction (OCR) |  | 2026-01-14 | 2026-01-15 | Eswar | Text Files | Done | bar: 2021-11-08 to 2021-11-09
|  |  | 2.2.1.1. Chunking Strategy (Size 1000) | 2026-01-16 | 2026-01-16 | Durga | Chunked JSON | Done | bar: 2021-11-10
3. System Development |  |  |  | 2026-01-19 | 2026-01-23 | Durga & Devesh | Beta App | Done | bar: 2021-11-11 to 2021-11-15
| 3.1. Backend Logic |  |  | 2026-01-19 | 2026-01-21 | Durga | Python Scripts | Done | bar: 2021-11-11 to 2021-11-13
|  | 3.1.1. RAG Pipeline Setup (LangChain) |  | 2026-01-19 | 2026-01-20 | Durga | Vector Store | Done | bar: 2021-11-11 to 2021-11-12
|  |  | 3.1.1.1. FAISS Index Implementation | 2026-01-20 | 2026-01-20 | Durga | Index File | Done | bar: 2021-11-12
|  | 3.1.2. Resume Screener Logic |  | 2026-01-21 | 2026-01-21 | Durga | Scoring Function | Done | bar: 2021-11-13
| 3.2. Frontend Integration |  |  | 2026-01-22 | 2026-01-23 | Devesh | Web UI | Done | bar: 2021-11-14 to 2021-11-15
|  | 3.2.1. Gradio Interface Design |  | 2026-01-22 | 2026-01-22 | Devesh | UI Layout | Done | bar: 2021-11-14
|  |  | 3.2.1.1. API Endpoint Integration | 2026-01-23 | 2026-01-23 | Devesh | Connected App | Done | bar: 2021-11-15
4. Testing & Closure |  |  |  | 2026-01-26 | 2026-01-30 | Sakshi & Swamy | Final Submission | Done | bar: 2021-11-16 to 2021-11-20
| 4.1. Quality Assurance |  |  | 2026-01-26 | 2026-01-27 | Sakshi | Test Report | Done | bar: 2021-11-16 to 2021-11-17
|  | 4.1.1. Prompt Engineering Tests |  | 2026-01-26 | 2026-01-26 | Sakshi | Optimized Prompts | Done | bar: 2021-11-16
|  |  | 4.1.1.1. Accuracy & Latency Check | 2026-01-27 | 2026-01-27 | Sakshi | Bug Fixes | Done | bar: 2021-11-17
| 4.2. Deployment & Documentation |  |  | 2026-01-28 | 2026-01-30 | Devesh | Final URL | Done | bar: 2021-11-18 to 2021-11-20
|  | 4.2.1. Hugging Face Spaces Deploy |  | 2026-01-28 | 2026-01-28 | Devesh | Live Link | Done | bar: 2021-11-18
|  |  | 4.2.1.1. Final Report & Video | 2026-01-29 | 2026-01-30 | Swamy | Project Files | Done | bar: 2021-11-19 to 2021-11-20